## Data
Date | Pool | ODEA Phase | Ritual | Artifact | Result | Link | Understand what people need | Address the whole experience, from start to finish | Make it simple and intuitive | Build the service using agile and iterative practices | Structure budgets and contracts to support delivery | Assign one leader and hold that person accountable | Bring in experienced teams | Choose a modern technology stack | Deploy in a flexible hosting environment | Automate testing and deployments | Manage security and privacy through reusable processes | Use data to drive decisions | Default to open
2015-06-20 | Two | Delivery | Sprint Planning | Plan | Review Product Backlog | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Discovery%20and%20Requirements%20Analysis.docx | X | X |  |  |  | X | X |  |  |  |  | X
2015-06-21 | Two | Delivery | Sprint Planning | Data Analysis | Review mapping of Epic 1 user stories to API data | https://github.com/binarygroup/OpenFDA/blob/master/Artifacts/Design%20Delivery.docx |  | X | X | X |  |  | X |  |  |  |  | X
2015-06-21 | Two | Delivery | Sprint Planning | Sprint Backog | Select Epic 1 user stories for Sprint Backlog | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx | X | X | X | X |  |  | X |  |  |  |  | X
2015-06-21 | Two | Delivery | Scrum Meeting | Technology Stack | Setup Ruby on Rails environment | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx |  |  |  |  | X |  | X | X |  |  |  |  | X
2015-06-20 | Two | Delivery | Scrum Meeting | Architecture | Assess using Kibana as extension of FDA elasticsearch | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx |  | X |  |  | X |  |  | X |  |  |  | X | X
2015-06-21 | Two | Delivery | Scrum Meeting | Technology Stack | Setup GitHub for team | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx |  |  |  |  | X |  |  | X |  |  | X |  | X
2015-06-21 | Two | Delivery | Scrum Meeting | Architecture | Leverage Kibana source as a reference and build on AngularJS | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx |  | X | X |  | X |  | X | X |  |  |  | X | X
2015-06-22 | Two | Delivery | Scrum Meeting | Analytical Mockup | Review Design Prototype v1 | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx | X | X | X | X | X |  | X |  |  |  |  | X
2015-06-24 | Two | Delivery | Scrum Meeting | Technology Stack | Setup AWS Elastic Beanstalk instance | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx |  |  |  |  | X |  | X | X | X
2015-06-24 | Two | Delivery | Scrum Meeting | Analytical Mockup | Review Design Prototype v1 | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx | X | X | X | X | X |  | X |  |  |  |  | X
2015-06-25 | Two | Delivery | Scrum Meeting | Technology Stack | Select Continuous Integration tool and leverage Elastic Beanstalk CM capabilities | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx |  | X |  | X | X |  | X | X | X | X | X |  | X
2015-06-29 | Two | Delivery | Scrum Meeting | User Testing | Arrange for user SME acceptance at Sprint Review | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx | X | X |  | X |  |  | X |  |  |  |  | X
2015-07-02 | Two | Delivery | Scrum Meeting | User Testing | Review Development Prototype changes | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx | X | X | X | X | X |  | X |  |  |  |  | X
2015-07-06 | Two | Delivery | Scrum Meeting | User Testing | Review Development Prototype changes | https://github.com/binarygroup/OpenFDA/blob/master/artifacts/Skype%20Discussion%20Thread.docx | X | X | X | X | X |  | X |  |  |  |  | X
2015-07-07 | Two | Delivery | Sprint Review | Acceptance Criteria | Review and accept Development Prototype | https://github.com/binarygroup/OpenFDA/blob/master/Artifacts/Design%20Delivery.docx | X | X | X | X | X |  | X |  |  |  |  | X

## Meta
Phases | Rituals | Artifacts | Tools | Pools
Discovery | User Story Development | Acceptance Criteria | Mozenda | One
Decision Strategy | Sprint Planning | Analytical Mockup | Tableau | Two
Delivery | Scrum Meeting | Architecture
Implementation | Sprint Review | Code
| Retrospect | Data Analysis
| Backlog Grooming | Database
| Release | Database Design
Decision
Enterprise Context
Installation Instructions
Interview
Monitoring Instrument
Plan
Product Backlog
Prototype
Script
Sprint Backog
Technology Stack
User Testing
Vision Statement