## Defects
# | Sprint Release # | Priority | Tab | Issue | Resolved?
1 | 1 | 1 | Report | The reporting Date filter has no effect but Kevin said wasn’t available yet. | yes
2 | 1 | 1 | Report | Drug filter has no effect on the results I filtered on one of the drugs but nothing in the bar chart changed as a result. It only shows what you selected with an ‘x’ so that you can remove the filter if you want. | yes
3 | 1 | 1 | Report | Same issue with the Patient outcome filter. | yes
4 | 1 | 1 | Report | The Age filter goes from 0 – 200. The filter (this applies to all of them) should only include the available values in the Db. So when I go to the Search Results chart and put in say 200, no records show up. Of course there aren’t any 200 years olds still alive and taking drugs! J | yes
5 | 1 | 1 | Report | The Weight filter should also only have a range of values that is available in the Db. Also, can we put on the filter whether the weight is in Kg or lbs? | yes
6 | 1 | 1 | Report | General: Title of the dashboard should reflect what the dashboard is reporting on. Robert - This is reflected in the attached screenshots. | yes
7 | 1 | 1 | Report | General: What is the Search field at the top of the report used for? Robert - Everything you type in returns an error – No matches found! | yes
8 | 1 | 2 | Report | General: Why are we showing Total Records at the top right part of the screen in large, bold text for? This places emphasis on that part of the screen and implies importance as compared to the rest of the visualization. I would place that type of information at the bottom of the visualization in much smaller text since it’s not a very important aspect of the visualization. | no
9 | 1 | 2 | Report | General: Each chart in the visualization should be titled. For example, I didn’t know what the bar chart was showing since it only has “count of events”, the %, and the timeline. The chart below that is called “Search Results” with filters that allow you to refine the results. I would rename that because the 1st thing I think of is that it was the results of whatever search term I entered at the top of the screen where you can perform a search in the search box. This area might be labelled Event Details. Also, how are these column filters interacting with the ones on the left-side of the screen? One more thing on the Search Result tabular chart. The gender column is shown as “1” or “2”. It should be Male or Female. When I try to filter on the Outcome column, I’m not getting any records by entering any of the outcomes I see on the left-side filter selection field. The other filters seem to work fine however. | no
10 | 1 | 2 | Report | General: Rafael - on the tooltip mouse hover for the bar chart, can you add the year represented in this chart, Robert - and say “in” rather than “on” the month? Rafael - Also, the legend shows a blue dot with month as the label. You can probably remove that legend altogether since it really doesn’t add any value. The x-axis label already shows us that this is a monthly total. | no
11 | 1 | 1 | Report | On Report 2, the name of the drug is not being displayed properly in the drug X event count display | yes
12 | 1 | 2 | Report 2 | Rafael - This looks pretty good in general. The only comment that’s not a repeat of my observations above is that for the Country chart, can we change the Y-axis label name to something like “Count of Reports” or “% of Reports”? Robert - actually, don’t think the Country chart really adds value unless you can actually see the list of the top 5 or 10 reporting countries. | yes
13 | 1 | 2 | Report 2 | General: This report seems to be what looks like our executive summary report chart since it has various aspect of the data shown in several charts. I would move this tab as the 1st tab and maybe label it as such. | no
14 | 2 | 1 | By Month | May want to change name of Search button to Apply Filters | yes
15 | 2 | 1 | By Month | Country names not sorted alphabetically, would be better if had actual country names vs 2 digit alpha code | yes
16 | 2 | 1 | By Month | Drug names not sorted alphabetically | yes
17 | 2 | 1 | By Month | A little hard to select and move age and weight sliders | yes
18 | 2 | 1 | By Month | Clicking reset doesn’t reset age and weight sliders, appears to reset the data views though
19 | 2 | 2 | By Month | Show date range on the Adverse Report, rename to Details Report
20 | 2 | 2 | By Month | Put a Reset and Apply Filters button at bottom of filters as well as on top, so you don’t have to scroll screen
21 | 2 | 2 | By Month | Apply button in Date Selection seems to be superfluous, results don’t change until you press Search button above. Would be more intuitive if you clicking on start and/or end date would apply them. Might be best now to just remove it.
21 | 2 | 2 | By Month | Title change suggestion for the Adverse Event Count bar chart. Change Title to "% of Adverse Event Occurance per Month" | yes
22 | 2 | 1 | Demographics | Selected a single outcome (Fatal) and applied filter, but a small set of outcomes appeared in outcome chart. | yes
23 | 2 | 1 | Demographics | Selected an age range (28-70) and applied filter, but a small set of events outside that range (71-80) appeared in age chart. | yes
24 | 2 | 1 | Demographics | Country chart is not really useful unless you can see countries that represent the bulk of the population. Can’t see that on X-axis underneath bars. | yes
25 | 2 | 2 | Demographics | Gender circle chart is bigger than Outcome circle chart, should be the same size to not emphaize one over the other | yes
26 | 2 | 1 | Demographics | Age Chart filter range goes from 14 - 110 however the chart shows age ranges 561 - 620 years. Remove the last two age ranges. | yes
27
28

## Labor Estimates
| Min/Max estimate (hrs) | Actual (hrs)
User Story: As a FDA/ Pharmaceutical Researcher I would like to determine if past adverse drug events can be correlated to a specific period of time, or if there are seasonal correlations such as the high point of the allergy season, so that I can further understand potential harmful drug effects and related public health risks. | 7 - 10 | 8
User Story: As a FDA/ Pharmaceutical Researcher I would like to determine if past adverse drug events can be correlated to one or more drugs the patients is receiving, so that I can further understand the potential harmful effects of those drugs and related public health risks. | 7 - 10 | 7
User Story: As a FDA/ Pharmaceutical Researcher I would like to determine if past adverse drug events can be correlated to the patient outcomes reported, so that I can further understand the potential harmful effects of one or more drugs and related public health risks. | 10 - 15 | 11
User Story: As a FDA/ Pharmaceutical Researcher I would like to determine if past adverse drug events can be correlated to demographics like a specific age range, a specific weight range, the gender or country of patients, so that I can further understand potential harmful drug effects and related public health risks | 15 - 20 | 14
User Story: As a FDA/ Pharmaceutical Researcher I would like to determine if past adverse drug events can be correlated to specific conditions of drug use like the cumulative dosage a drug patient received before having a reaction, the drug’s lot number, the form the drug was delivered (tablet, liquid, etc.) and the frequency of dosage, so that I can further understand the potential harmful effects of prescriptions for that drug and related public health risks. | 15 - 20 | 17
User Story: As a FDA/ Pharmaceutical Researcher I would like to determine if past adverse drug events can be correlated to the reporter’s occupation, so that I can further understand potential harmful drug effects and related public health risks. | 7 - 10 | 8
Write tests for API-calling methods | 2 - 5 | 3
Set up continuous integration | 2 - 4 | 3
Set up app server and deployment (PaaS) | 3 - 5 | 4
Set up continuous monitoring | 1 - 2 | 1
Miscellaneous configuration and set up | 3 - 8 | 5
Total |  | 81